## Sheet1
| 3 - 7 October |  |  |  |  | 10 - 14 October |  |  |  |  | 17 - 21 October |  |  |  |  | 24 - 28 October |  |  |  |  | 31 Oct - 4 Nov |  |  |  |  | 7 - 11 November |  |  |  |  | 14 - 18 November |  |  |  |  | 21 - 25 November |  |  |  |  | 28 - 30 Nov
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W
Resource Planing and Work Division
Assignment of Work | bar: 3 - 7 October M
Web-Frontend Development
Skeleton Code | bar: 3 - 7 October T to 24 - 28 October T
Web-Page Desgining | bar: 10 - 14 October W to 7 - 11 November W
Adding Responsivness | bar: 14 - 18 November T to 28 - 30 Nov W
Web-Backend Development
Routing the Path | bar: 3 - 7 October T to 10 - 14 October F; 14 - 18 November F to 21 - 25 November T
Integrating ML | bar: 7 - 11 November M to 14 - 18 November F
Establising the Connection frontend | bar: 17 - 21 October M to 17 - 21 October F
Web Security | bar: 24 - 28 October M to 31 Oct - 4 Nov F; 21 - 25 November M to 21 - 25 November F
Data Collection
Raw Data Collection | bar: 3 - 7 October T to 10 - 14 October F
Backend Development
Module Training | bar: 17 - 21 October M to 17 - 21 October F
Increasing Accuracy | bar: 24 - 28 October M to 31 Oct - 4 Nov F
Setup Connection with Web Backend | bar: 7 - 11 November M to 14 - 18 November F